## Introduction
ISDP371 – SS4: Assignment 4
TEST PLAN
Campus | Centurion Campus
Group name | Digital Innovators
Group members | 24301606 – Letsoalo; Lerato 23301264 – Masemola; Unathi 24301501 – Mosoma; Tebogo 24301467 – Mulamba; Benjamin
Project title | Big Little Things Foundation – Volunteer and Donations Management System
Document | Test Plan (Assignment 4)
Repository | https://github.com/Lerato-Letsoalo/Big-Little-Things-Foundation-System
1. Introduction
This Test Plan sets out how the Digital Innovators team will test the Volunteer and Donations Management System that is being built for the Big Little Things Foundation. The plan covers the period from the start of development through to full system testing, and is aligned with the project's iterative development schedule (see Project Proposal, Section 1.7: Project Schedule) and with the modules described in the System Design Specification. Testing will take place in three development iterations, each covering a related group of system modules. During each iteration the team will perform one unit test to confirm that a specific piece of functionality works correctly, and one usability test based on Jakob Nielsen's ten usability heuristics, to confirm that the interface built during that iteration is understandable and easy to use for volunteers, administrators and public visitors. This gives a minimum of six tests across the three iterations, in line with the assignment requirement. Once all modules have been developed and integrated, the team will carry out one comprehensive System Test. This test will validate the functionality, performance and usability of the complete, integrated solution against the functional and non-functional requirements defined in the User Requirements Document (URD), rather than testing modules in isolation. Each test in this plan lists the iteration it belongs to, the type of test, the module(s) or feature(s) being tested, the planned test date, and the team member(s) responsible for carrying it out. Test results, evidence and detailed test cases will be recorded in the accompanying Unit Test, Usability Test and System Test templates and referenced from the GitHub repository.
2. Testing Approach Summary
Stage | Test(s) conducted | Purpose
Iteration 1 | 1 Unit Test + 1 Usability Test | Verify core public website and volunteer registration functionality and usability.
Iteration 2 | 1 Unit Test + 1 Usability Test | Verify volunteer hour logging, donation capture and related interfaces.
Iteration 3 | 1 Unit Test + 1 Usability Test | Verify admin dashboard, certificate generation and reporting functionality and usability.
System Test | 1 comprehensive System Test | Validate the fully integrated system against functional and non-functional requirements.
See the 'Test Plan' sheet for the full, detailed schedule of all tests.

## Test Plan
Test Plan – Big Little Things Foundation Volunteer and Donations Management System
Digital Innovators ¦ ISDP371 – SS4: Assignment 4
Test ID | Iteration | Test type | Module / Feature tested | Test objective | Test date | Team member(s) responsible | Test method / tool | Status
T1 | Iteration 1 | Unit Test | Volunteer Registration & Authentication (FR1, FR2, NFR1) | Verify that a public visitor can successfully register as a volunteer with valid data, that invalid/incomplete data is rejected with correct validation messages, and that a registered volunteer can log in securely with a hashed password. | 2026-08-26 | Tebogo Mosoma (supported by Unathi Masemola) | Manual functional testing of the registration form and login screen against defined test cases; results recorded on the Unit Test template. | Completed
T2 | Iteration 1 | Usability Test | Public Website (Home, About Us, Projects, Volunteer pages) | Evaluate the public website against Nielsen's usability heuristics (e.g. visibility of system status, match between system and real world, consistency and standards, aesthetic and minimalist design) to confirm the site is easy for a first-time visitor to understand and navigate. | 2026-08-26 | Unathi Masemola (supported by Tebogo Mosoma) | Heuristic walkthrough of the high-fidelity prototype/website using a Nielsen heuristics checklist; issues logged with severity ratings on the Usability Test template. | Completed
T3 | Iteration 2 | Unit Test | Volunteer Hour Logging & Donation Capture (FR4, FR8, FR11) | Verify that a logged-in volunteer can log hours for an attended event and that the hours are saved with a 'Pending' status, and that an administrator/donor can capture a monetary or physical donation with the amount, date and status recorded accurately. | 2026-09-02 | Lerato Letsoalo (supported by Tebogo Mosoma) | Manual functional testing of the hour-logging form and donation entry form against defined test cases, including boundary and invalid-input cases; results recorded on the Unit Test template. | Completed
T4 | Iteration 2 | Usability Test | Volunteer Dashboard & Donation/Payment Flow | Evaluate the volunteer dashboard and the donation/payment journey against Nielsen's heuristics (e.g. user control and freedom, error prevention, help users recognise and recover from errors) to confirm volunteers and donors can complete key tasks without confusion. | 2026-09-02 | Benjamin Mulamba (supported by Unathi Masemola) | Heuristic walkthrough and task-based review (e.g. 'log 2 hours for an event', 'make a R100 donation') using a Nielsen heuristics checklist; issues logged on the Usability Test template. | Completed
T5 | Iteration 3 | Unit Test | Certificate Generation & Reporting Dashboard (FR5, FR10, FR11, NFR3) | Verify that an approved volunteer's total hours automatically trigger a downloadable certificate with the correct details, and that the administrator reporting dashboard correctly calculates and displays volunteer hour and donation totals per city/project. | 2026-09-09 | Benjamin Mulamba & Tebogo Mosoma | Manual functional testing of the certificate-generation trigger and dashboard report figures against known seeded data; results recorded on the Unit Test template. | Completed
T6 | Iteration 3 | Usability Test | Admin Dashboard (Volunteers, Donations, Projects, Approvals) | Evaluate the administrator dashboard against Nielsen's heuristics (e.g. visibility of system status, recognition rather than recall, flexibility and efficiency of use) to confirm administrators can efficiently approve hours, manage donations and monitor statistics. | 2026-09-09 | Unathi Masemola (supported by Lerato Letsoalo) | Heuristic walkthrough of the admin dashboard using a Nielsen heuristics checklist, with administrator-role test account; issues logged on the Usability Test template. | Completed
T7 | System Test | System Test | Full Integrated System (Public Website + Volunteer Portal + Admin Portal) | Validate the complete, integrated system end-to-end against the functional requirements (FR1–FR17) and non-functional requirements (NFR1–NFR11) in the URD, covering functionality, security/RBAC, performance (page load and dashboard refresh times), responsiveness across devices, and overall usability. | 2026-09-12 | All group members: Tebogo Mosoma, Lerato Letsoalo, Unathi Masemola, Benjamin Mulamba | End-to-end functional, performance and responsiveness testing across all three user roles (public user, volunteer, administrator), plus a consolidated Nielsen heuristics review; results recorded on the System Test template and summarised in the Assignment 4 report. | Completed
Key:
Iteration 1 | Front-end development – Public website & Volunteer registration/authentication (per Project Schedule)
Iteration 2 | Back-end development – Volunteer hour logging & Donation/payment module (per Project Schedule)
Iteration 3 | Admin dashboard, certificate generation & reporting module (per Project Schedule)
System Test | Conducted once the full system is implemented and integrated
Note: Detailed test cases, steps, expected/actual results and outcomes for each test above are recorded in the separate Unit Test, Usability Test and System Test Excel templates, and evidence is stored in the project GitHub repository.

## Nielsen Heuristics Checklist
Nielsen's 10 Usability Heuristics – Reference Checklist
Used as the guideline for all Usability Tests (T2, T4, T6) and the System Test (T7) usability review.
# | Heuristic | What to check | Pass / Fail
1 | Visibility of system status | The system keeps users informed through appropriate feedback (e.g. loading indicators, confirmation messages after registering, donating or logging hours) within reasonable time. | Pass
2 | Match between system and the real world | The system speaks the users' language with familiar words, phrases and concepts (e.g. 'Log Volunteer Hours', 'Make a Donation') rather than technical jargon. | Pass
3 | User control and freedom | Users can easily undo/redo actions or leave an unwanted state (e.g. cancel a donation, edit a submitted form before final submission, clear navigation back to previous pages). | Pass
4 | Consistency and standards | Wording, layout, icons and actions are consistent across the public website, volunteer portal and admin dashboard, following standard web conventions. | Pass
5 | Error prevention | The design prevents problems before they occur (e.g. form validation before submission, confirmation before deleting a project or gallery item). | Pass
6 | Recognition rather than recall | Options, actions and information are visible or easily retrievable, minimising the user's memory load (e.g. visible menu items, dashboard summaries instead of remembered figures). | Pass
7 | Flexibility and efficiency of use | The interface caters to both novice public users and experienced administrators, e.g. shortcuts or bulk actions for frequent admin tasks. | Pass
8 | Aesthetic and minimalist design | Pages contain only relevant information; unnecessary elements do not compete with the content users actually need (e.g. dashboard cards, donation forms). | Pass
9 | Help users recognise, diagnose and recover from errors | Error messages are expressed in plain language, precisely indicate the problem, and suggest a solution (e.g. invalid donation amount, failed login). | Pass
10 | Help and documentation | Where needed, help is easy to find, task-focused and not overly large (e.g. FAQ page, tooltips, contact support option). | Pass
Source: | Nielsen, J. 1994. 10 Usability Heuristics for User Interface Design. Nielsen Norman Group. Available at: https://www.nngroup.com/articles/ten-usability-heuristics/